## Sheet1
SR.NO | Activity | Activity Driven By | Current Date | Current Status(Working Part) | Blockers | Steps Taken to Resolve | Target Date
1 | Set Up WordPress Locally | Team 6 | 2021-11-13 | WordPress working properly after locally hosted to all of our system |  |  | 2021-11-13
2 | Feasibility Study Discussed | Team 6 | 2021-11-14 | The modules are set to be tested, decided the test cases for GUI Automation and REST API. |  |  | 2021-11-14
3 | GUI(WordPress login) | Santanu & Samarjit | 2021-11-15 | Implementing the login feature(launching the login page using driver,validate the page title) | Can't fetch the data from .csv file | Add the proper dependency | 2021-11-16
4 | API(User Authorization) | Sanchari, Kushal and Bristi | 2021-11-15 | Implementing the user authorization(along with negative testcases) |  |  | 2021-11-15
5 | GUI(WordPress login) | Santanu & Samarjit | 2021-11-16 | Data fetching from the .csv file is working properly and login feature is also working properly along with negative testcases |  |  | 2021-11-16
| GUI(WordPress Posts) |  |  | Started working on post module | A miniwindow popup is coming and can't able to close | Handled with try/catch | 2021-11-17
6 | API(Posts module) | Sanchari, Kushal and Bristi | 2021-11-16 | Started creating the requests on post module(such as performing CRUD operation) | Problem in Schema Validation | Using the Tiny Validator | 2021-11-17
7 | GUI(WordPress Posts) | Samarjit | 2021-11-17 | Miniwindow Popup is handled and New post is created | Problem in fetching data for contents of new post from .csv file | By adding Tab | 2021-11-17
|  | Sanchari | 2021-11-17 | working on category panel in post module(such as create category) |  |  | 2021-11-17
8 | GUI(WordPress Pages) | Santanu | 2021-11-17 | started working on page module(such as create page,view page) |  |  | 2021-11-17
9 | API(Post Module) | Sanchari and Bristi | 2021-11-17 | Schema of the post module is validated successfully and started working on media module |  |  | 2021-11-17
10 | API(Categories Module) | Kushal | 2021-11-17 | Started working on categories module | Problem in category creation due to server issue |  | 2021-11-18
11 | Meeting with support Mentor | Team6 | 2021-11-18 | Give some suggestions(such as POM model structure, testng report, ppt) |  |  | 2021-11-18
12 | GUI(WordPress Posts) | Samarjit | 2021-11-19 | Create a post without creating category and also after creating category | Problem in category selection | Scroll bar, tab and enter key press | 2021-11-20
13 | GUI(WordPressPost-Publish) | Kushal | 2021-11-19 | Publish and view post section is working properly |  |  | 2021-11-19
14 | GUI(WordPress Pages) | Santanu | 2021-11-19 | Completed the page module successfully(implementing delete page feature) | recurrsion problem | by locating bulk dropdown window | 2021-11-19
| GUI(WordPress Media) | Santanu and Bristi | 2021-11-19 | Media Module is working | Apply button is not working and alert popup is coming | Resolved by making some chganges in the code | 2021-11-19
15 | API(Pages Module) | Sanchari and Santanu | 2021-11-19 | All the features are working properly, implementing global variables and set environment variable |  |  | 2021-11-19
16 | API(Categories Module) | Kushal and Bristi | 2021-11-20 | All the features of categories are working and the server issue is resolved |  |  | 2021-11-20
17 | GUI(WordPress Posts) | Samarjit and Santanu | 2021-11-20 | Categories selection during creating post is working properly |  |  | 2021-11-20
18 | GUI(WordPress with all test modules) | Samarjit and Santanu | 2021-11-20 | All the features of all modules are working properly(with POM,DDT,TestNG) |  |  | 2021-11-20
19 | API(Media Module) | Sanchari and Samarjit | 2021-11-21 | Media module is working properly |  |  | 2021-11-21
20 | PPT | Team6 | 2021-11-21 | Started working on ppt |  |  | 2021-11-22